## Slide 1
NYHDIF
HSCN: Migration Update & Key Messages
Dan Parry – HSCN Programme Manager (North)

## Slide 2: N3 to HSCN:
N3:
  Designed to enable NHS organisations to access national applications
  National private network
  Single supplier
  Long-length contract arrangement
HSCN:
  Designed to support Paperless 2020 and the Five Year Forward View
  Standards-based approach that will:
      Enable interoperability between Health and Care organisations
      Support regional collaboration
      Create a competitive marketplace
      Support flexible and remote working patterns
    Make better use of existing infrastructure and services

## Slide 3: State of Play: Yorkshire & Humber
North Yorkshire: NYNET
Yorkshire & Humber : YHPSN
Independent Self-Serve
Awarded – 100%
Call-Off – 32%
Savings between 35% – 70%
Migrations Complete – 5%
Total Circuits – 1,131
Leading nationally in migrations to HSCN
11% of total N3/TN Estate
North East AP – Awarded

## Slide 4: NHS Digital’s Role:
CNSP
NHS Digital HSCN
Field Force
NHS Digital HSCN
Deployment Office
Sharing of Intelligence
Consumer Liaison
Management Information
(Contracted)
Migration Forecasting
Migration Progress Reporting
Migration Completion
HSCN Consumer
(Inc. DA)
Collaborative Engagement
Collaborative Engagement
Call-Off
Technical Design
Ordering & Planning
Installation & Migration
Migration Scheduling
YHPSN
NYNET
(NE AP*)
Supporting Consumers

## Slide 5: NHS Digital - Key Messages:
Driving prompt and successful HSCN procurement:
A diverse supplier market for HSCN services is in place and level of competition is good – 23 CNSP are ready to sell across the market place
Lots of organisations have already concluded procurement for HSCN. Those who haven’t are in the minority. (Yorkshire & Humber make up 12% of the TN/N3 estate).
If not already done, you should initiate HSCN Call-Off & Order Process no later than end December 2018 to avoid a loss of connection.
Voice and Video overlay services will not be supported over HSCN and you need to replace/cease.
50% of the migrations to date have been within Yorkshire & Humber - without significant issue, so you can be confident in your migration.
Forecast tells us that a queue to migrate will begin forming soon. The best way to minimise impact and safeguard your preferred migration date, will be to plan and progress your migration early.

## Slide 6: NHS Digital - Key Messages:
Achieving efficiencies and value for money:
Consumers are reminded to enter into a Call-Off to obtain accurate pricing based on technical design.
Efficiencies: compare like for like for efficiencies but look for opportunities to modernise/rationalise your network.
Direct Award outside of the YHPSN Framework/NYNET (or North East AP) may place your devolved funding at risk.
NHS Digital engage directly with suppliers where performance requires improvement through the HSCN Deployment Office.
A number of suppliers across the market are engaged in non-competitive behaviour – this is against the spirit of HSCN and compliance status.

## Slide 7: NHS Digital - Key Messages:
Vacating the Transition Network (N3):
Legacy Transition Network will be gradually decommissioned between now and 31 August 2020.
Closing the 51 points of presence (PoPs), that make up the Transition Network, this year.
Cessation dates for each PoP are based on procurement and migration plans provided by your organisations earlier this year.
The target cease dates effectively sets you’re the date you need to migrate by – RAG Status Letters
Keeping PoPs provisioned longer than planned costs money that could otherwise be devolved locally.
If you were require TN connectivity after this point, you may be required to cover the costs of provisioning PoPs that could otherwise be ceased.
NHS Digital (HSCN Programme) are here to support consumers migrating from TN to HSCN.

## Slide 8: PoP Closure Letters (Amber/Green RAG):

## Slide 9: PoP Closure Letters (RED RAG):

## Slide 10: NHS Digital - Key Messages:
Service Award
Order Received (Call-Off)
Order Confirmed
Migration Scheduled
Migration Complete
Service Ceased
We have observed customers taking 4 – 12 weeks to call-off orders
From point of order receipt it can take 4-8 weeks to confirm an estimated delivery date for the service (dependent on site survey requirements)
We expect suppliers to raise migration slot requests 3-5 weeks ahead of the planned migration. The actual booking slot will typically occur 1-2 weeks after the service is deployed and tested.
BT requires ~10 working day notice for migrations so they will take place 2-3 weeks after they are scheduled.
Customers are typically issuing cease notifications 2-3 weeks post migration completion. These can take a further 20-30 days to be processed by BT.
4-12 weeks
4-8 weeks
1-2 weeks
2-3 weeks
5-7 weeks
Service Deployed
9-13 weeks
HSCN services will typically take 9-13 weeks to deliver depending on the availability of capacity in the ground.
Min. | Mid. | Max.
25 wks | 35 wks | 45 wks
Migration Journey:
Migrating earlier increases the flexibility of migration slots (e.g. out of hours).
Increased support available for earlier migrations whilst the national programme is not at full capacity

## Slide 11: NHS Digital - Key Messages:
Pre Call-Off/Order
Call-Off/Order
Awaiting Order Processing
Preparing for Migration
Migration
Post Migration/Cease
HSCN Field Force (WebEx) for Consumers – Monthly
Opportunity for consumers to ask HSCN Field Force questions/request support around any part of the process, YHPSN Rep plus guest speaks (Consumers) and lessons learnt
Funding & Migration Support and Guidance
Customer FAQs
Field Force Escalation Point
Requirements Gathering
Migration Guidance
Customer FAQ
Field Force Escalation Point
Migration Support and Guidance
Progress tracking
Migration Checklist
Customer FAQ
Escalation Point
Call-off tracking
Migration Support & Checklist
Customer FAQ
Field Force Escalation Point
Migration Support & Checklist
Migration Tracking
Customer FAQ
Field Force Escalation Point
Migration Guidance
Cease Reminders
Customer FAQ
Field Force Escalation Point
Overlay Notification & Options (if required)
Overlay Replacement Support (if appropriate) and monitoring cessation of overlay in advance of migration
Deployment Office
Supporting Consumers:
HSCN Field Force to support N3/HSCN Consumers throughout the process:
FIELD FORCE

## Slide 12
YHPSN: dale.coombs@leeds.gov.uk

## Slide 13
NHYDIF – YHPSN Key Messages
Engage with Redcentric and enter in to a “Call Off” with Redcentric to see the potential transformation, rationalisation and cost savings that can be achieved by your organisation.
Entering into a “Call Off” with Redcentric does NOT commit you to procure services from them, it creates a contract which provides non-disclosure terms to both parties and allows you hold Redcentric to service levels for quotations, solution designs and other activities that they have committed to under the framework.
The YHPSN framework has more services available than HSCN or COIN replacement, organisations are using other services to transform their services using Managed Firewall, consolidating Internet Services, Connectivity Solutions for Service Users Home’s, VPN two factor authentication and moving other services to the Redcentric core network not only to make savings but increase resilience and availability
The YHPSN framework does have a price list (which is the maximum that can be paid for each service) however in most cases when organisations engage the price they are quoted is below the list price so assessing the potential savings needs to be done by engaging with Redcentric.
The YHPSN TRT (Transition Resource Team) is there to provide support to YHPSN partners, the TRT is independent of Redcentric and is happy to meet with partners either with or without Redcentric present to help achieve the maximum value from the new regional framework.

## Slide 14
NHYDIF – YHPSN Contacts
The YHPSN partnership is currently focused on new regional framework but that is not its sole purpose, the partnership is to drive forward projects and initiatives that will benefit partners. All public sector organisations are welcome to join the partnership even if they are part of another consortium for network services, YHPSN is about more than just networks.
Please do not hesitate to make contact if you have any queries or require more information about the new regional framework or YHSPN Partnership.
Thank you for you time today
Dale Coombs - HSCN Migration Manager
Dale.Coombs@leeds.gov.uk
07891 275711

## Slide 15
Questions? daniel.parry1@nhs.net