PAPER B

Information Governance Sub-Group

Yorkshire & Humber Area Strategic Information Governance Network (SIGN)

- The table below lists the follow up actions from the Y & H Information Governance Steering Group.

- Please could you provide a statement in the “Progress” column to provide an update regarding your actions in order to provide assurance to the Information Governance Sub Group that actions have been completed and / or provide an update on the progress to date?

| MINUTE | ACTION POINTS | PROGRESS | Action Owner | Action Completed |
| --- | --- | --- | --- | --- |
| November 2018 |  |  |  |  |
| 6 | IG Education/Personal Development Updates | Attending Cyber training course – feedback to group Dec Update – did not attend, will complete online in 2019. | HH |  |
| 7 | Data Security & Protection Toolkit | Pseudonimisation Audit – set up working group Dec Update – to take place on 17/12/18 – confirmed John Hodgson from NHS Digital has agreed to attend | SMe |  |
| 8 | Confidentiality, Data Protection and Freedom of Information re: Data Sharing Agreements (DSAs) | forward Tier 3 example to Chair for group circulation Dec Update – will forward to Chair | PW |  |
|  |  | group to share examples with the rest of the Group - forward to Chair for group circulation Dec Update - ongoing | ALL |  |
|  |  | Raise at next SIGN Chairs meeting Dec Update - Nov SIGN Chairs meeting ran over and issue was not raised – will raise at next meeting | SMe |  |
| 10 | AOB | New NHSD IG Training Package – agreed to forward his modified version to Chair for group circulation Dec Update - ongoing | DS |  |
| December 2018 |  |  |  |  |
| 4 | Data Protection Legislation | NHS Mail – accessing/storing emails – DBH Guidance – to forward to Chair upon completion for circulation to group | RU |  |
| 8 | Confidentiality, Data Protection and Freedom of Information re: Brexit and Data Flows (EEA) | Document (read to group) re NHS Guidance on data flows - to forward a copy to the Chair for circulation to the group. | PW |  |
| JANUARY 2019 |  |  |  |  |
| 3 | Action Points (Paper B) | Forward to Chair any issues you want raising at the next SIGN Chairs meeting on 1/2/19 | ALL |  |
| 4 | Data Protection Legislation: - Privacy Notices | Forward link to CQC Privacy Statement, to Chair to circulate to group for their information. https://www.cqc.org.uk/about-us/our-policies/privacy-statement | DS |  |
|  | - SARs | NHS Mail lack of contract variation regarding data processing – non-GDPR compliant – raise at next SIGN Chairs meeting on 1/2/19 | CHAIR |  |
| 8 | Confidentiality, Data Protection and Freedom of Information | FOI - second reading in parliament on 25/1/19 which is mostly for local government, but includes safeguarding children, contact with public authorities, ICO, etc – to send notification to Chair for circulation to the group. https://beta.parliament.uk/work-packages/vmZhj7uU | AN |  |
| 9 | Data and IT /Information Security | Connecting for Health for Guidance re: recording of prisoners – to provide link or details to circulate to the group. | TOM |  |