## SIGN Action Log 2020.2021
Yorkshire & Humber Area Strategic Information Govenerance Network (SIGN) Action Log
Action ID | Date added to tracker | Forum issue/concern raised | Action | Progress Update | Nominated Lead | Action Owner | Status
17 | 2020-09-10 |  | Training for the group - SMe to see what is available for the group | 12/11/2020 SMe will explore this further in the New Year 14/01/2021 SMe asked the group for suggestions and to send her details 13/05/2021 SMe to pick up 08/07/2021 NHSX are arranging some specialised IG training 12/08/2021 The YHIG Group in September has 3 guest speakers - contact Helen Jones, YAS if you would like to attend |  | SMe | Open
39 | 2020-12-10 |  | Minecraft not working with Windows 10 - Raise at National SIGN | 14/01/2021 SMe to raise at the National SIGN 11/03/2021 No further update 13/05/2021 No further update 08/07/2021 Staff member has not come back to KR for an update |  | SMe | Open
50 | 2021-04-08 |  | Inter-Agency Sharing Protocal - JP toreview and feedback to the group | 08/07/2021 Awaiting feedback from JP 12/08/2021 On hold at present due to other pressures |  | JP | Open
53 | 2021-05-13 |  | Future Meetings - Details to SMe | 10/06/2021 Going forward look at having some sessions where we get presenters 08/07/2021 The group preferred the SIGN meeting via MS Teams 12/08/2021 Re-arranged the time of the meeting due to the clash with NHSD O365 meeting, possibly change in day for 2022 |  | All | Open
59 | 2021-08-12 |  | DSPT Assertion 10 - MM/JC to meet outside this meeting |  |  | JC/MM | Open
60 | 2021-08-12 |  | SOP to be produced for the YHCR Audits |  |  | JC | Open
61 | 2021-08-12 |  | DPST 'Standards not met - plan agreed' ask CAG regardining application |  |  | JC | Open
62 | 2021-08-12 |  | SYB ICS - IG Lead opportunity - details to SMe to forward on |  |  | CB/SMe | Open
64 | 2021-08-12 |  | Cohort concern - update when received |  |  | JP | Open
65 | 2021-08-12 |  | Cohort concern - send email trail to Sheffield and RDASH |  |  | JP | Open
66 | 2021-08-12 |  | Cohort concern - SMe to raise at National SIGN |  |  | SMe | Closed

## Sheet3 (hidden)
Open
Closed
All

## Closed Actions
Yorkshire & Humber Area Strategic Information Govenerance Network (SIGN) Action Log
Action ID | Date added to tracker | Forum issue/concern raised | Action | Progress Update | Nominated Lead | Action Owner | Status
1 | 2020-06-11 |  | Further clarification on sending antibody results out from the National Group |  |  | SM | Closed
2 | 2020-06-11 |  | NHS Mail Data Breach - SMe to forward details she has received |  |  | SMe | Closed
3 | 2020-07-09 |  | Corrections to minutes 11/06/2020 |  |  | NG | Closed
4 | 2020-07-09 |  | North Yorkshire Safeguarding Adults Boards (HYSB) JP to NL a copy of the 3M document |  |  | JP | Closed
5 | 2020-07-09 |  | Data Breaches - NHS Charities MD, JP to share information |  |  | JP | Closed
6 | 2020-07-09 |  | Digital Staff Passport - PW attending a meeting on 12/07/2020 and will share information with SMe | 08/10/2020 Trust's have left with their ESR Leads |  | PW | Closed
7 | 2020-07-09 |  | SIRO Webinar - Bookings to CM |  |  | CM | Closed
8 | 2020-07-09 |  | Office 365 to be added to future agendas |  |  | NG | Closed
9 | 2020-07-09 |  | MS Teams - inviting patients as a gues, BJ/CM to send guidance for circulation |  |  | BJ/CM | Closed
10 | 2020-08-13 |  | Centrally manage Opt Out Policy - JC to feedback to the board and share forms from Leeds | 08/10/2020 JC gave feedback and amended the service level agreement |  | JC | Closed
13 | 2020-08-13 |  | YHCR Agreements | 10/09/2020 These have been updated anr re-issued |  | JC | Closed
14 | 2020-08-13 |  | DPIA Guidance - RU to send to the group | 10/09/2020 RU to check with CR to see if this can be shared |  | RU | Closed
15 | 2020-08-13 |  | SARS to be added to the September agenda | 10/09/2020 SARS discussed further |  | NG | Closed
18 | 2020-09-10 |  | DSPT - 20/21 October baseline SMe to email JH | JH confirmed the removal October baseline, this is now under 'news' on the DSPT website 12/11/2020 DSPT 20/21 Still not been released, awaiting further clarification over the assertion relating to Cyber Essentials Plus |  | SMe | Closed
19 | 2020-09-10 |  | List of items outside the EU, CB to email GN |  |  | CB | Closed
21 | 2020-10-08 |  | Add Ernest Attah, Data Security Sepecialist to the distribution list |  |  | NG | Closed
22 | 2020-11-12 |  | Circulate the latest slides from the YHCR |  |  | SMe | Closed
23 | 2020-11-12 |  | Share the letter sent to CAG with the group | 10/12/2020 NL to send copy of the CAG letter to SMe 14/01/2021 Letter shared with the group |  | JC | Closed
24 | 2020-11-12 |  | Share amended letter template with the Group |  |  | CB | Closed
25 | 2020-11-12 |  | Share the link from the ICO site |  |  | SMe | Closed
26 | 2020-11-12 |  | DSPT - 20/21 October release | 27/11/2020 Update DSPT 20/21 to be released 30/11/2020 |  | SMe | Closed
27 | 2020-11-12 |  | Circulate the latest slides from the NHSX Webinar |  |  | SMe | Closed
29 | 2020-11-12 |  | Set up a Sub Group Meeting for 365 | 01/12/2020 First 365 Sub group Meeting took place, book another meeting shortly after 16 December 2020. |  | NG | Closed
30 | 2020-11-12 |  | Circulate Whitelist contact | 10/12/2020 SMe to contact BJ for the whitelist contact |  | BJ | Closed
31 | 2020-11-12 |  | KRo to share her organisations Information Asset Owners handbook |  |  | KRo | Closed
32 | 2020-11-12 |  | RA Meeting to be set up with key people |  |  | NG | Closed
34 | 2020-12-10 |  | Amend SR organisation on November minutes |  |  | NG | Closed
35 | 2020-12-10 |  | Circulate redaction information |  |  | SR | Closed
36 | 2020-12-10 |  | Additions to the 19/20 DSPT to be forwarded to JH directly | 14/01/2021 Group currently working towards February baseline on DSPT 20/21 |  | All | Closed
37 | 2020-12-10 |  | Circulate the latest slides from the NHSX Webinar |  |  | SMe | Closed
38 | 2020-12-10 |  | FAQs for Lateral Flow Testing - share with the group |  |  | TM | Closed
40 | 2021-01-14 |  | Violence Reduction - West Yorks, slides to be shared |  |  | SMe | Closed
42 | 2021-01-14 |  | PW to share Data Notification Mapping Form | 11/02/2021 PW to forward to SMe for circulation around the group |  | PW | Closed
43 | 2021-01-14 |  | JH to share IG posters |  |  | KH | Closed
11 | 2020-08-13 |  | YHCR Future Questions | 10/09/2020 Future questions to be brought to this group 08/10/2020 RU has asked how patients will know and how to opt out - need further clarification, not turning on until patients know and understand the process 14/01/2021 SMe to contact JC for an update 11/03/2021 - Close |  | All | Closed
12 | 2020-08-13 |  | IG Leads contacted across the Y&H region | 10/09/2020 PW has still not been contacted 08/10/2020 PW has still not been contacted 10/12/2020 PW to contact JC directly. GN reported that the ISA had been sent through to the CCGs. 14/01/2021 Project Team are contacting organisations directly 11/03/2021 Close |  | All | Closed
16 | 2020-09-10 |  | Red Tape - SIGN to be involded with reviewing the guidance documents. SMe to raise at the National SIGN | 12/11/2020 SMe raised at the National SIGN regardining the regional SIGNS being involved with reviewing guidance. 10/12/2020 SMe to see if this is raised at the National Group next week. 14/01/2021 Red Tape is on the next National Group agenda 11/03/2021 Close |  | SMe | Closed
20 | 2020-09-10 |  | Office 365 queries, raise at the group so SMe can push up to NHSD via the National SIGN | 08/10/2020 Various issues that keep getting discovered by organisations 12/11/2020 SMe has pushed this up to the National SIGN, organisations are out of the loop, this will be raised with NHSX 10/12/2020 The 1st Sub Group Meeting was held on 01 December 2020 14/01/2021 Continue to work collaboratively, Colin Parke to join the 365 Sub Group. 14/01/2021 Group to email SMe and 365 queries to raise with NHSD 11/03/2021 Seperate 365 group & NHS Digital live events - close |  | SMe | Closed
28 | 2020-11-12 |  | Further updates guidance from NHSX | 01/12/2020 SMe contacted NHSX for an update on NIMS/NIVS. Mo further update, the guidance is still awaiting approval and the DPIAs are still been updated. 10/12/2020 Still awaiting DPIAs and Guidance 14/01/2021 DPIAs for NIMS/NIVs are owned by NHSE, organisations are already sending data 11/03/2021 Organisations to request a copy of the DPIA - Close |  | SMe | Closed
44 | 2021-02-11 |  | DSPT Assertion Queries - to be discussed at the sub group meetings | 11/03/2021 Close |  | All | Closed
45 | 2021-02-11 |  | Add RU presentation on the skills network to the next agenda | 11/03/2021 Close |  | NG | Closed
47 | 2021-04-08 |  | DTAC Webinar - Details to follow | 13/05/2021 Close |  | NG | Closed
48 | 2021-04-08 |  | Information Sharing Gateway demonstration - Details to follow | 13/05/2021 Close |  | NG | Closed
49 | 2021-04-08 |  | NHS.scot - KR to forward NHSD reponse | 13/05/2021 Close |  | KR | Closed
33 | 2020-11-12 |  | Information Sharing Gateway | 10/12/2020 Look at this in the New Year 14/01/2021 Add to the next SIGN agenda 11/02/2021 Invite back to SIGN for an update 11/02/2021 Seperate meeting for an update 08/04/2021 HIGA Information Sharing Gateway session 23/04/2021 all welcome to attend, SIGN Information Sharing Gateway session scheduled for 11/05/2021 - meeting invite to follow 13/05/2021 Any comments to Sandip 10/06/2021 IGSG Event 11/06/2021, SMe to email details, MS asked organisations to register Close |  | SMe | Closed
41 | 2021-01-14 |  | DSPT Queries | 11/02/2021 JH was on the NHSX webinar - Audit requirements are huge, any queries can be sent directly to JH so he can raise these 11/03/2021 Any audit concerns to be raised with John Hodson 13/05/2021 John Hodson to attend a future meeting 10/06/2021 John Hosdson attended meeting today - Close |  | SMe | Closed
46 | 2021-04-08 |  | YHIGG - If you would like to join send your details to Helen Hartland | 13/05/2021 Currently in the process of setting up the September meeting, please send any detail to HH 10/06/2021 Close |  | All | Closed
51 | 2021-05-13 |  | Data Protection by Design Template to be circulated | 10/06/2021 Close |  | KRo | Closed
52 | 2021-05-13 |  | Money lost to fraud details to be circultated | 10/06/2021 Close |  | RMc | Closed
55 | 2021-06-10 |  | 3rd Party mail services - Email CB with providers/challenges | 08/07/2021 Close |  | All | Closed
57 | 2021-07-08 |  | DSPT - NL to send NG presentation to circulate | 09/07/2021 Close |  | NL | Closed
54 | 2021-06-10 |  | NHSD Feedback - SMe to speak to JH | 12/08/2021 Close |  | SMe | Closed
56 | 2021-07-08 |  | Right to be Forgottoen - CB to send TM template letter | 12/08/2021 CB sent TM a template letter |  | CB | Closed
58 | 2021-07-08 |  | DSPT - JH to atttend SIGN in August | 09/08/2021 NG has had no response from JH, possibly due to annual leave 12/08/2021 JH attended the SIGN meeting to give a DSPT update |  | NG | Closed
63 | 2021-08-15 |  | JH to send presentation for circulation | 13/08/2021 NG circulated JH presentation - Close |  | JH/NG | Closed